## Read me
Risk register - Quillfield Systems Inc. (fictional)
Simulated scenario for a learning and portfolio project. No real company, client or audit.
Likelihood (L) and impact (I) on a 1-5 scale; score = L x I (formulas).
Inherent = before any controls. Current residual = with controls as they operate today. Target residual = after the treatment plan is complete.
Rating bands: 1-4 Low, 5-9 Medium, 10-15 High, 16-25 Critical.
Likelihood: 1 Rare (less than once in 5 years), 2 Unlikely, 3 Possible (once in 1-3 years), 4 Likely (about once a year), 5 Almost certain (already happening or several times a year).
Impact: 1 Minimal, 2 Minor (internal only), 3 Moderate (one customer affected or contract breach), 4 Major (several customers, regulator notification, SOC 2 exception), 5 Severe (customer financial loss, lost enterprise deal, widespread data exposure).

## Risk register
Risk ID | Risk description | Linked controls | Gap ref | Inherent L | Inherent I | Inherent score | Inherent rating | Current L | Current I | Current residual score | Current rating | Treatment | Treatment plan | Owner role | Target date | Target L | Target I | Target residual score | Target rating
R-01 | Leaver, contractor or generic accounts stay active and are used to access customer data or systems without authorization. | AC-01; AC-03; AC-04; AC-05 | G-03; G-04; G-05 | 4 | 4 |  |  | 3 | 4 |  |  | Mitigate | Add contractors to BambooHR with end dates; automate disable via BambooHR-Entra provisioning; assign owners to or remove generic accounts; first quarterly UAR in Q4 2026. | IT Administrator | 2026-12-23 | 2 | 4
R-02 | Phishing or credential theft leads to account takeover, helped by MFA exclusions and no phishing-resistant MFA for admins (a mailbox compromise already occurred in May 2026). | AC-02; HR-02; OPS-03 | G-02; G-06 | 5 | 4 |  |  | 4 | 4 |  |  | Mitigate | Empty CA-Exclusions except break-glass; move service accounts to workload identities; require phishing-resistant MFA for admin roles; enrol contractors in training. | Director, IT & Security | 2026-11-25 | 2 | 4
R-03 | Standing privileged access in Entra ID or the production subscription is misused or compromised, allowing tenant-wide or production-wide changes. | AC-05; AC-06 | G-03; G-06 | 4 | 5 |  |  | 3 | 5 |  |  | Mitigate | Onboard Global Admin, Privileged Role Admin and Azure Owner/Contributor to PIM with approval; reduce Global Admins to 4; rotate and own service principal secrets. | Director, IT & Security | 2026-12-18 | 1 | 5
R-04 | A fraudulent or mistaken edit to a customer's payee bank details in the internal admin console redirects customer payments to the wrong account. | AC-07; OPS-03 | G-07 | 4 | 5 |  |  | 3 | 5 |  |  | Mitigate | Require second-person approval for bank detail edits in the admin console; restrict the permission to a named group; Sentinel rule and weekly review of the edit log until dual approval ships. | VP Engineering | 2027-01-22 | 1 | 5
R-05 | An unreviewed or unauthorized change reaches production (infrastructure repo without branch protection, direct portal changes, self-approved deployments) and causes an outage or weakens security. | CHG-01; CHG-02; CHG-03; AC-07 | G-13; G-07 | 4 | 4 |  |  | 3 | 4 |  |  | Mitigate | Apply the standard ruleset to platform-infra; remove admin bypass; enable prevent self-review; move engineers to PIM-eligible access; monthly review of non-pipeline write operations. | DevOps Lead | 2026-12-23 | 2 | 4
R-06 | A known critical vulnerability in internet-facing or production components is exploited before it is fixed. | OPS-01; MON-02; CHG-04; AC-10 | G-09 | 4 | 5 |  |  | 3 | 5 |  |  | Mitigate | Approve remediation SLAs and an exception process; clear criticals older than 30 days; fix and retest the open pen test high finding; monthly ageing report to leadership. | Security Engineer | 2027-01-22 | 2 | 5
R-07 | An intrusion goes undetected or is detected late because key logs are missing, retention is 90 days, and alerts are triaged slowly with no notes. | OPS-02; OPS-03 | G-10 | 4 | 4 |  |  | 3 | 4 |  |  | Mitigate | Connect GitHub, AKS and Key Vault logs; set 12-month retention (archive tier); define triage SLA and closure reason codes; add after-hours paging for high severity. | Security Engineer | 2027-01-22 | 2 | 4
R-08 | A security incident is handled poorly and Quillfield misses the 72-hour customer notice in the MSA or its PIPEDA breach reporting and record-keeping obligations. | OPS-04 | G-11 | 3 | 5 |  |  | 3 | 4 |  |  | Mitigate | Approve IR plan with a PIPEDA breach assessment step and breach record log; run a tabletop; complete a retrospective review of the May 2026 incident. | Director, IT & Security | 2026-12-18 | 2 | 4
R-09 | Customer data is lost or the service is down for an extended period because backups have never been restored and there is no DR plan. | OPS-05; BCP-01 | G-12 | 3 | 5 |  |  | 3 | 4 |  |  | Mitigate | Set PITR to 35 days and monthly LTR; enable Blob versioning; perform and document a restore test; write a DR runbook with RTO/RPO and test it. | CTO | 2027-01-22 | 2 | 4
R-10 | A vendor or subprocessor breach exposes Quillfield or customer data, with no due diligence done and weak contractual remedies. | VND-01; VND-02; VND-03 | G-14 | 3 | 5 |  |  | 3 | 5 |  |  | Mitigate | Tier all vendors; collect and review SOC 2 reports for Tier 1; file or sign DPAs with Atlassian and the QA firm; add a security tier field as a required step for new vendors in NetSuite. | Controller | 2027-01-22 | 2 | 4
R-11 | Customer data is exposed from staging, which holds unmasked production copies and is accessed by an offshore contractor through a shared login. | CONF-03; VND-02; AC-05 | G-15; G-14 | 4 | 5 |  |  | 4 | 5 |  |  | Mitigate | Stop production-to-staging refreshes now; purge existing copies; build masked or synthetic data set; replace shared SQL login with named Entra accounts. | VP Engineering | 2026-11-25 | 1 | 5
R-12 | Customer data is kept after contract termination, breaching the MSA and the PIPEDA limiting-retention principle. | CONF-02 | G-15 | 5 | 3 |  |  | 5 | 3 |  |  | Mitigate | Write a deletion runbook; delete the 4 churned customers' data after legal confirms no hold; add a quarterly check of churned customers. | VP Engineering | 2027-01-22 | 1 | 3
R-13 | Confidential data leaks through anonymous sharing links, unlabelled documents or unmanaged contractor devices. | CONF-01; CONF-04; AC-12; RISK-02 | G-15; G-08 | 4 | 4 |  |  | 3 | 4 |  |  | Mitigate | Disable 'Anyone' links and expire existing ones; publish sensitivity labels; move DLP to enforce mode; require compliant devices or app protection for contractors. | IT Administrator | 2027-01-22 | 2 | 3
R-14 | Malware or ransomware on an endpoint spreads to corporate files or developer credentials. | AC-12; OPS-01; OPS-05 | G-08; G-09 | 4 | 4 |  |  | 2 | 4 |  |  | Mitigate | Onboard the 7 macOS laptops to Defender; enforce patch compliance; cyber insurance partly transfers financial impact. | IT Administrator | 2026-11-25 | 2 | 3
R-15 | The SOC 2 Type I is delayed or qualified because controls have no owner oversight, policies are unapproved and there is no risk assessment, putting the enterprise contract at risk. | GOV-01; GOV-03; RISK-01; MON-01 | G-01 | 4 | 4 |  |  | 4 | 4 |  |  | Mitigate | Approve policies; start quarterly leadership security review; accept this risk register; run quarterly control self-assessment; readiness re-check in February 2027. | CEO | 2027-02-26 | 2 | 4

## Heat map (current)
Count of risks by current likelihood (rows) and impact (columns)
L \ I | 1 | 2 | 3 | 4 | 5
5
4
3
2
1